## Slide 1: Toro Park Pilot Project Doug Bilse, TE Project Manager
Notes: How many were here October 8?
Review attendance dots

## Slide 2
Severe Hwy 68 Congestion=
Cut-Thru Traffic
Toro Park Pilot Project

## Slide 3: Portola Drive Cut-Through Traffic

## Slide 4
Severe Portola Congestion=
Cut-Thru
Cut-Thru Traffic
Toro Park Pilot Project

## Slide 5: Cut-Through Cut-Through Traffic

## Slide 6
Call to action!

## Slide 7: Project Schedule
21 Feb.
HOA asks for pilot project
3 Apr.
Community Kick-off Meeting
3 Apr. – 22 May
3 Committee Meetings
22 May
Community Consensus Meeting
26 June
TAMC funds Pilot Project
12 July
Phase I installed
25 July
School asks for a redesign of Drop-Off
7 Aug.
Opening day of school with improvements
27 Sep.
Phase II installed

## Slide 8
Blocking the cut-through traffic route?
Scenic Route 68 Corridor Improvement Project
528 Trips in AM Peak

## Slide 9
Phase I:
Close Re-Entrance Point at Torero Drive
Scenic Route 68 Corridor Improvement Project
528 Trips in AM Peak

## Slide 10
AM Peak Hour
Cut-Thru Traffic Solved!
Toro Park Pilot Project

## Slide 11
Other Projects Rerouted Traffic to Hwy 68
Toro Park Pilot Project

## Slide 12: Yes We Needed Phase II

## Slide 13
Phase II:
Close Portola Dr. Entrance from Hwy 68
152 Trips in AM Peak

## Slide 14
Phase II:
Close Portola Dr. Entrance from Hwy 68
152 Trips in AM Peak

## Slide 15: Pilot Project Feedback: Data Collection and Community Engagement
7 Aug.
First Day of School
7 Aug. – 20 Sept.
Monitor
8 Oct.
Community Workshop
27 Sept.
Phase II install
Oct. 1-Oct. 8
Monitor
23 Oct.
TAMC Board Meeting
Jan 15
Community Workshop
Jan 22
TAMC Board Meeting
July 12
Phase I installed
July 30
Monitor
November 8
Monitor

## Slide 16: Toro Park Pilot Project Travel Time Runs
Route | Baseline target | Worse for school traffic | Worst for Hwy 68 | Current Trend
 | Phase I |  | Phase II | 
 | Davis Closed |  |  | Davis Open
 | Before School Opens | School Open |  | 
 | Signals Uncoordinated | Bad timing plan |  | Better Signal timing plan
Portola: Torero-Hwy 68 | 2:15-2:26 | 2:30-15:54 | 2:25 | 2:35-6:10
Hwy 68: Portola-Torero | 3:14-9:18 | 8:06-12:35 | 20:31 | 3:18-6:36
Typical Loop | 8:00 | 12:00 | 23:16 | 9:00
Worst Loop | 11:00 | 24:00 | 23:16 | 11:46

## Slide 17: Toro Park Pilot Project Travel Time Runs
Route | Baseline target | Worse for school traffic | Worst for Hwy 68 | Current Trend
 | Phase I |  | Phase II | 
 | Davis Closed |  |  | Davis Open
 | Before School Opens | School Open |  | 
 | Signals Uncoordinated | Bad timing plan |  | Better Signal timing plan
Portola: Torero-Hwy 68 | 2:15-2:26 | 2:30-15:54 | 2:25 | 2:35-6:10
Hwy 68: Portola-Torero | 3:14-9:18 | 8:06-12:35 | 20:31 | 3:18-6:36
Typical Loop | 8:00 | 12:00 | 23:16 | 9:00
Worst Loop | 11:00 | 24:00 | 23:16 | 11:46

## Slide 18: October 8 Community Workshop Results

## Slide 19
59%
37%

## Slide 20: We Heard You Loud and Clear!
Phase I doesn’t work for West Toro or school
Phase II is too close to Creekside residences
Congestion limited to a few hours- solution should be too!
Fund permanent improvements
Make it look nice
Notes: How can we do better?

## Slide 21: Phase I: Torero Drive Relocation

## Slide 22: Torero Drive Relocation: No Gate
Busses Only
Buss & cars
School Traffic Only

## Slide 23: Torero Drive Relocation: With Gate
Busses Only
Buss & cars
School Traffic Only

## Slide 24: January 15 Workshop Results Torero Drive Partial Road Closure
Relocate closure to School Entrance: |  | 
 | All | 64%
 | West Toro Park | 70%
Install gates when possible: |  | 
 | All | 85%
 | West Toro Park | 75%
Remove road closures/Kill project: |  | 
 | All | 8%
 | West Toro Park | 16%

## Slide 25
Phase II:
Relocate Creekside

## Slide 26
Relocate Creekside
No Gate

## Slide 27
Relocate Creekside
With Gate

## Slide 28: January 15 Workshop Results Creekside Partial Road Closure
Relocate closure to School Entrance: 89%
Install gates when possible: 82%
Remove closures/Kill project: 10%

## Slide 29: How do we fund this?
Include safe routes to school features
Include multimodal path
Tie improvements into State Route 68 Roundabout Project
Notes: New years resolution
Make good decisions quickly
Dry January

## Slide 30: ADA Multi-Use Path School to Fort Ord National Monument & Laguna Seca
Raised Crosswalk at school entrance

## Slide 31: Multi-Use Path

## Slide 32: Where do you live, and do you support a Multi-Use Trail?
Do you like the idea of constructing a formal trail so that all users can enjoy it (ADA accessible)?
90% agree
Should it connect the school to the Fort Ord National Monument parking lot?
84% agree

## Slide 33: Most important votes from January 15 workshop
Are we heading in the right direction?
  YES
If we install gates at new locations, is adding 8-12 minutes to morning trips to Monterey Peninsula a fair trade-off for eliminating cut-thru traffic?
  YES
Did we hear you?
  YES

## Slide 34: What is left?
Get feedback from TAMC Board on January 22
Hand off project to County Public Works
Complete technical report and submit to County Public Works
Coordinate work with County staff to implement interim solutions
Work towards funding permanent solutions as part of SB-1 grant

## Slide 35: Recommendations for Technical Study
Relocate Phase I Partial Road Closure to School Entrance
Relocate Phase II Partial Road Closure Closer to Fire Station
Research and implement movable barricades (gates)
Upgrade devices to create a residential character
Work with County staff on a 6-month transition plan using remaining funds

## Slide 36: Questions

## Slide 37
Raised Crosswalk
Crosswalk

## Slide 38: Add Graph of traffic counts

## Slide 39: Criteria for Partial Road Closure
Must block cut-through traffic during AM Peak Hours
One must maintain access to school without forcing parents to make a left turn from Hwy 68 to Torero Drive
One must be east of fire station
Must be at an intersection
Design vehicle (FedEx truck) must be able to make a U-Turn
Ideally there is general agreement on location
Looking at Bus-Activated gate option for long-term alternative to partial road closure

## Slide 40: What is traffic doing to our community? Quality of Life issues
45 minutes to drop off students (stress)
Safety on side streets (roads not designed for this type of traffic)
Speeding, aggressive drivers and hostility (can’t walk peacefully in the mornings)
Feel land-locked
Need to reschedule appointments because can’t exit driveway or use Portola Drive
Noise (don’t need a clock to know when school starts)
Commercial trucks have no business on our streets
Emergency response
Home values suffer from congestion

## Slide 41: Portola Drive: Cut-Through Traffic 15-Min Counts

## Slide 42: Attachment 3: Phase II (Creekside)

## Slide 43: What Happens If You Ignore the Signs?

## Slide 44: BEFORE
152 Trips
22 Trips
0 Trips
24 Trips
AFTER

## Slide 45: BEFORE
704 Trips
528 Trips
1232 Trips
0 Trips
AFTER

## Slide 46: Attachment 2: Phase I (Torero Drive/Bravo Court)

## Slide 47: Make it look nice!

## Slide 48: What Happened Since October 8 Workshop?
Caltrans traffic signals coordinated better on Highway 68
Caltrans continues work implementing adaptive/AI signals
Caltrans rejected idea to relocate the merge from current location to east of Portola Interchange
Davis Road was re-opened
Meet with stakeholders to identify feasible alternatives
TAMC collected traffic data